## Info
Info: | A planning document that supports the Homicide Prediction Research Project
Analytical team: | Risk Assessments Data Science, Data & Analysis, Ministry of Justice
Main Stakeholders: | Probation Reform Programme, Ministry of Justice
Main contact: | REDACTED
Last updated: | September 2023
Relevant documents:
DPIA 5443 | REDACTED
DPIA 5468 | REDACTED
Business case | REDACTED
DPIA GMP | REDACTED
DSA GMP | REDACTED
Movement Form 1 | REDACTED
Movement Form 2 | REDACTED
Project tools:
Trello board | REDACTED
Github | REDACTED
Confluence page | REDACTED

## Timeline
|  | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June
| Activity | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025
Working Group Meetings
| Introduction (Communication by email) | January: February 2023
| Target variable and cohort definition | January: March 2023
| Modelling and data linking approaches | January: July 2023
| Preliminary results based on MOJ data only | January: December 2023
| Decision on using local police data | January: March 2024
| Ethics board | January: July 2024
| Results | January: October 2024
| Formal presentation to the group | January: December 2024
Admin (high priority; to do asap)
A1 | Apply for SC clearance | bar: January to March
A2 | Apply for NPPV clearance renewal | bar: February to April
A3 | DPIA MOJ - Stage 1 | bar: January
A4 | DPIA MOJ - Stage 2 | bar: January to June
A5 | Business Case MOJ | bar: February to May
A6 | DPIA GMP | bar: February to June
A7 | DSA GMP | bar: March to June
A8 | Data movement form MOJ | bar: May to July
A9 | Data movement form GMP | bar: August to September
A10 | Data movement form MOJ | bar: October
A11 | Final report | bar: October to December
A12 | Publication | [24 empty] | r | r | r | r | r | r | bar: November to December
A13 | Ensure all ToCs in DPIA are met in terms of data retention | bar: December
Phase 0A: Initial discoveries (completed)
B1 | Data discovery - Oasys, Delius, Nomis | bar: January to February
B2 | Review model solutions from internal hackathon and kaggle (based on MOJ data only) | bar: February to March
B3 | Investigate important features in models | bar: February to March
B4 | Define target variable | bar: January to April
B5 | Define cohort | bar: February to April
B6 | Decide cut-off date for collecting predictive and target variables | bar: March to April
Phase 0B: MOJ Data gathering
C1 | Cohort spine | bar: February to April
C2 | MOJ Datasets | March: →; April: →; May: →; June: →; July: a; September: r; October: r; January: r; February: r
C3 | PNC Terminal | February: →; March: →; April: →; May: a; October: r
C4 | Combine all MOJ Data | May: →; June: →; July: a; October: r; February: r
Phase 0C: Baseline calculations (using RSR-SNSV; optional when to complete)
D1 | Model discovery - Segmentation Dataset | bar: October
D2 | Replicate RSR-SNSV calculations on cohort | bar: November to January
Phase 1: Internal data modelling (new approaches / features)
E1 | Initial analysis and feature exploration | bar: January; March; May
E2 | Initial model discovery and selection | bar: May to July
E3 | Decision on project metrics and evaluation | bar: May to July
E4 | Initial model prototyping | bar: June to August
E5 | Data transfer 1 | bar: June
E6 | Data linking, Anonymisation and Data transfer 2 | bar: June to July
E8 | Model prototyping | bar: August to November
E9 | Show and tell | bar: November
E10 | Ethics log | bar: October to December
E11 | Preliminary report | bar: November to December
Phase 2A: Data discovery - GMP
F1 | MOJ visit GMP | bar: February to March
F2 | Agree list of variables | bar: May
Phase 2B: Data transfer
G1 | Data transfer 3 - via data uploader | bar: September; November
G2 | Data discovery - GMP data | bar: September to October
G3 | Splink data linking | bar: September to October
G4 | Data transfer 4 | bar: November
G5 | Data linking, Anonymisation and Data transfer 5 | bar: November
Phase 3: Internal + GMP data modelling
H1 | Data discovery - combined data | bar: November to December
H2 | Initial analysis and feature analysis | bar: November to January
H3 | Model prototyping | bar: December to May
H4 | Ethics log | bar: January to March
H5 | Intermediate report | bar: February to March
H6 | Final Report | bar: September to November
H7 | Publication date | [29 empty] | r